## 🏠 COVER
📊 camsroy.com
Smart Finance Templates ¦ Built for Indian SMEs, CAs & Service Businesses
PROJECT PROFITABILITY TRACKER
Is This Project Actually Making Money — and Where Will It End Up?
Budget vs Actual · Forecast at Completion · Margin Erosion Alert · Dynamic RAG Status
Project / Client Name | [Enter Project Name]
Business / Firm Name | [Your Firm Name]
Financial Year | FY 2025-26
Prepared By | [Your Name]
Report Date | [As-on Date]
📋 WORKBOOK NAVIGATION
📋 | PROJECT SETUP — Client details, contract value, team members and billing/cost rates
⏱ | TIME TRACKER — Hours budgeted vs actual vs forecast — billing efficiency and unbilled hours
💸 | COST TRACKER — Budget vs Actual vs Forecast to Complete vs EAC by category — the core tracker
📊 | PROJECT P&L — Full P&L: contracted revenue, costs, GM% — Budget vs Actual vs Forecast
🚦 | DASHBOARD — RAG status, forecast GM%, cost overrun, billing efficiency — one-page summary
📖 | HOW TO USE — Step-by-step guide, formula explanations, how CA firms vs agencies should use this
🎨 COLOUR LEGEND
Blue cells = Input (enter your data here)
Green = Calculated output — auto-updates
Gold = Key metric / decision output
Red = Overrun / margin below threshold
Yellow = At risk / watch closely
💡 WHAT THIS TEMPLATE ANSWERS
✓ | Is this project going to make money — not just historically, but forecast at completion?
✓ | Where exactly is the margin being lost — staff, subcontractors, or expenses?
✓ | Are we billing efficiently — how many hours are logged but not yet billed?
✓ | What is the Estimated Cost at Completion vs what we budgeted when we won this project?
✓ | Dynamic RAG status — Green/Amber/Red on margin, cost, billing, and schedule simultaneously
✓ | Works for CA firms, IT companies, agencies, contractors — anyone billing project or time-based work
© camsroy.com ¦ Free for personal & commercial use ¦ www.camsroy.com

## 📋 PROJECT SETUP
📋 camsroy.com ¦ PROJECT SETUP — Identity, Contract Value & Team Rates
Enter once. All other sheets reference these. Blue cells = Input.
🪪 A. PROJECT IDENTITY
Field | Value | Notes
Project / Engagement Name | ERP Implementation — Rajesh Traders | As it appears on your contract/SOW
Client Name | Rajesh Traders Pvt Ltd | Legal name for invoicing
Project Type | Fixed Fee | Fixed Fee / T&M / Retainer / Mixed
Project Manager | Priya Sharma | Internal owner of this project
Contract / SOW Reference | SOW-2025-047 | For document tracking
Start Date | 2025-04-01
Planned End Date | 2025-09-30
Revised Forecast End Date | 2025-10-15 | Update as project progresses
💰 B. CONTRACT & BUDGET
Parameter | Value | Notes
Contracted / Quoted Value (₹, ex-GST) | 1200000 | Total contract value excluding GST
GST Rate on Services | 18% | 18% for most professional services
Total Contract Value incl. GST (auto) | 1416000 | Auto-calculated
Budgeted Cost at Quote / Pricing Stage (₹) | 780000 | Your cost estimate when you priced and won this project. Compare to Cost Tracker grand total budget row — they should match.
Budgeted Gross Margin ₹ (auto) | 420000 | Contract Value - Budgeted Cost
Budgeted Gross Margin % (auto) | 35% | The GM% you expected when you won this
Minimum Acceptable GM% (threshold) | 25% | RAG turns red if forecast GM% falls below this. Set Billing Efficiency Target in row below.
Cost Tracker Grand Total Budget (auto, from Cost Tracker) | 881000 | Must equal B19 — if different, reconcile your cost tracker budget entries.
👥 C. TEAM & BILLING RATES (up to 7 members)
Team Member | Role | Billing Rate (₹/hr) | Cost Rate (₹/hr) | Budgeted Hours | Budgeted Revenue (₹) | Budgeted Cost (₹)
Priya Sharma | Project Manager | 3500 | 1500 | 80 | 280000 | 120000
Arjun Mehta | Senior Consultant | 2800 | 1200 | 120 | 336000 | 144000
Divya Rao | Business Analyst | 2000 | 900 | 100 | 200000 | 90000
Karan Singh | Developer | 1800 | 800 | 150 | 270000 | 120000
Ananya Gupta | QA Analyst | 1500 | 700 | 60 | 90000 | 42000
|  | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0
TOTALS |  |  |  | 510 | 1176000 | 516000
ℹ Billing Rate = what you charge the client per hour. Cost Rate = what this person costs your firm (salary/12/working hours). If billing is Fixed Fee (not T&M), leave Billing Rate blank and only track Cost Rate and Hours for cost monitoring. ¦ © camsroy.com

## ⏱ TIME TRACKER
⏱ camsroy.com ¦ TIME TRACKER — Hours Budgeted vs Actual vs Forecast
Blue = Input (actual hours logged, remaining estimate). All other columns calculate automatically from Project Setup rates.
⏱ HOURS & BILLING TRACKER
Team Member | Role | Billing Rate (₹/hr) | Cost Rate (₹/hr) | Budget Hours | Actual Hours | Remaining (Est.) | Forecast Total Hrs | Variance (Hrs) | Revenue Billed (₹) | Cost Actual (₹) | Cost Forecast (₹)
Priya Sharma | Project Manager | 3500 | 1500 | 80 | 72 | 10 | 82 | -2 | 252000 | 108000 | 123000
Arjun Mehta | Senior Consultant | 2800 | 1200 | 120 | 108 | 15 | 123 | -3 | 302400 | 129600 | 147600
Divya Rao | Business Analyst | 2000 | 900 | 100 | 85 | 18 | 103 | -3 | 170000 | 76500 | 92700
Karan Singh | Developer | 1800 | 800 | 150 | 130 | 22 | 152 | -2 | 234000 | 104000 | 121600
Ananya Gupta | QA Analyst | 1500 | 700 | 60 | 52 | 10 | 62 | -2 | 78000 | 36400 | 43400
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTALS |  |  |  | 510 | 447 | 75 | 522 | -12 | 1036400 | 454500 | 528300
📊 BILLING SUMMARY
Total Budgeted Revenue (hrs × billing rate) | 1176000 | [6 empty] | What you planned to bill for all team hours
Total Revenue Billed to Date (actual hrs × rate) | 1036400 | [6 empty] | Actual billing earned so far
Total Revenue at Forecast Completion | 1204000 | [6 empty] | Forecast billing at completion — compare to contracted value
Billing Efficiency % (Actual / Budget Hours) | 87.65% | [6 empty] | Below 80% = significant unbilled time
Unbilled Hours (Budget - Actual, if positive) | 63 | [6 empty] | Hours budgeted but not yet logged — opportunity to bill
ℹ Actual Hours and Remaining Estimate are the only inputs here. Everything else is calculated. For Fixed Fee projects, focus on cost columns K and L rather than revenue columns. ¦ © camsroy.com

## 💸 COST TRACKER
💸 camsroy.com ¦ COST TRACKER — Budget · Actual · Forecast to Complete · EAC
Blue = Input. EAC = Actual + Forecast to Complete. Variance = Budget - EAC (positive=under, negative=overrun).
👥 A. DIRECT STAFF COST
Cost Category | Budget (₹) | Actual to Date (₹) | Forecast to Complete (₹) | Est. at Completion (₹) | Variance (₹) | Variance (%) | Status
Staff / Team Cost (from Time Tracker) | 516000 | 454500 | 73800 | 528300 | -12300 | -2.384% | 🔴 Overrun
Additional Staff / Freelancer (manual) | 80000 | 65000 | 20000 | 85000 | -5000 | -6.25% | 🔴 Overrun
SECTION A TOTAL | 596000 | 519500 | 93800 | 613300 | -17300 | -2.903% | 🔴 Overrun
🤝 B. SUBCONTRACTORS & OUTSOURCED WORK
Cost Category | Budget (₹) | Actual to Date (₹) | Forecast to Complete (₹) | Est. at Completion (₹) | Variance (₹) | Variance (%) | Status
Subcontractor 1 (Cloud Setup Partner) | 120000 | 95000 | 25000 | 120000 | 0 | 0% | 🟡 At Risk
Subcontractor 2 (Data Migration Vendor) | 80000 | 80000 | 0 | 80000 | 0 | 0% | 🟡 At Risk
Subcontractor 3 | 0 | 0 | 0 | 0 | 0 | 0% | —
SECTION B TOTAL | 200000 | 175000 | 25000 | 200000 | 0 | 0% | 🟡 At Risk
✈ C. DIRECT EXPENSES
Cost Category | Budget (₹) | Actual to Date (₹) | Forecast to Complete (₹) | Est. at Completion (₹) | Variance (₹) | Variance (%) | Status
Travel & Accommodation | 25000 | 18000 | 8000 | 26000 | -1000 | -4% | 🔴 Overrun
Software / Tools / Licenses | 15000 | 12000 | 3000 | 15000 | 0 | 0% | 🟡 At Risk
Materials / Consumables | 5000 | 3500 | 1500 | 5000 | 0 | 0% | 🟡 At Risk
Other Direct Expenses | 10000 | 6000 | 4000 | 10000 | 0 | 0% | 🟡 At Risk
SECTION C TOTAL | 55000 | 39500 | 16500 | 56000 | -1000 | -1.818% | 🔴 Overrun
🏢 D. OVERHEAD ALLOCATION
Cost Category | Budget (₹) | Actual to Date (₹) | Forecast to Complete (₹) | Est. at Completion (₹) | Variance (₹) | Variance (%) | Status
Overhead Allocated (firm-wide costs apportioned to project) | 30000 | 25000 | 8000 | 33000 | -3000 | -10% | 🔴 Overrun
TOTAL PROJECT COST | 881000 | 759000 | 143300 | 902300 | -21300 | -2.418% | 🔴 Overrun
ℹ Blue = Input. EAC = Actual to Date + Forecast to Complete (your current best estimate of remaining cost). Variance = Budget - EAC: positive means under budget, negative means overrun. Staff Cost in Section A links automatically from the Time Tracker — no manual entry needed. ¦ © camsroy.com

## 📊 PROJECT P&L
📊 camsroy.com ¦ PROJECT P&L — Revenue · Costs · Margin: Budget vs Actual vs Forecast
All figures auto-populate from Cost Tracker and Time Tracker. Only Invoiced and Collected rows need manual input.
💰 A. REVENUE
Line Item | Budget (₹) | Actual to Date (₹) | Forecast at Completion (₹) | Variance (₹) | Notes
Contracted / Quoted Value (ex-GST) | 1200000 |  | 1200000 |  | Fixed Fee: uses contract value. T&M: uses forecast hrs × billing rate from Time Tracker.
Invoiced to Date (ex-GST) |  | 850000 |  | -350000 | Enter actual invoiced amount
Collected / Received to Date |  | 720000 |  | -130000 | Variance = Collected - Invoiced (negative = outstanding debtors)
Remaining to Invoice |  | 350000 |  |  | Contracted value not yet invoiced
💸 B. COSTS (from Cost Tracker)
Line Item | Budget (₹) | Actual to Date (₹) | EAC (₹) | Variance (₹) | Notes
Direct Staff Cost | 596000 | 519500 | 613300 | -17300 | From Time Tracker + manual staff
Subcontractors | 200000 | 175000 | 200000 | 0 | Outsourced work
Direct Expenses | 55000 | 39500 | 56000 | -1000 | Travel, tools, materials
Overhead Allocated | 30000 | 25000 | 33000 | -3000 | Firm-wide cost apportionment
TOTAL PROJECT COST | 881000 | 759000 | 902300 | -21300
📈 C. GROSS MARGIN — THE KEY NUMBERS
Metric | Budget | Actual to Date | Forecast at Completion | vs Budget | Notes
GROSS MARGIN (₹) | 319000 | 91000 | 297700 | -21300 | Budget GM vs Forecast GM ₹ difference
GROSS MARGIN (%) | 26.58% | 10.71% | 24.81% | -1.775% | Based on billed revenue only — can appear high early in project. Use Forecast GM% (col D) as the primary decision metric.
Margin Erosion vs Budget |  |  | -10.19% |  | 🔴 Below minimum threshold
ℹ Column D (Forecast at Completion) is THE key number — it tells you where the project will end up, not where it is today. Margin Erosion = Forecast GM% minus Budget GM%. Any negative number means this project will be less profitable than you planned. ¦ © camsroy.com

## 🚦 DASHBOARD
🚦 camsroy.com ¦ PROJECT PROFITABILITY DASHBOARD
All metrics auto-populate. No manual entry needed on this page.
PROJECT IDENTITY
Project Name | ERP Implementation — Rajesh Traders
Client | Rajesh Traders Pvt Ltd
Project Manager | Priya Sharma
Start Date | 2025-04-01
Planned End Date | 2025-09-30
Forecast End Date | 2025-10-15
Days Elapsed / Total Planned Days | 290.7% |  | 🔴 Past planned end date
KEY FINANCIAL METRICS
Forecast GM% at Completion | 24.81% |  | THE key number — where this project will end up
Margin Erosion vs Budget | -10.19% |  | Negative = worse than budgeted
Total Cost Variance (₹) | -21300 |  | Positive=under budget, negative=overrun
Billing Efficiency % | 87.65% |  | Actual hrs / budget hrs
Invoiced to Date (₹) | 850000
Remaining to Invoice (₹) | 350000
Collected to Date (₹) | 720000
COST TRACKER SUMMARY
Category | Budget | Actual | EAC | Status
Staff Cost | 596000 | 519500 | 613300 | 🔴 Overrun
Subcontractors | 200000 | 175000 | 200000 | 🟡 At Risk
Direct Expenses | 55000 | 39500 | 56000 | 🔴 Overrun
Overhead | 30000 | 25000 | 33000 | 🔴 Overrun
TOTAL | 881000 | 759000 | 902300 | 🔴 Overrun
ALERTS & RECOMMENDED ACTIONS
Margin Status | 🔴 Forecast margin below minimum threshold — immediate review needed
Cost Status | 🔴 Overall cost overrun of Rs.21,300 — escalate immediately
Billing Status | 🟢 Billing efficiency on track (88% vs 80% target)
Invoice Action | 📋 Outstanding to invoice: Rs.350,000 — raise invoice

## 📖 HOW TO USE
📊 camsroy.com ¦ HOW TO USE — Project Profitability Tracker
STEP-BY-STEP GUIDE
Step 1 — PROJECT SETUP (fill once per project)
Enter project identity, contract value, GST rate, and team details. The Budgeted GM% and Budgeted Revenue auto-calculate. Set your Minimum Acceptable GM% threshold — this drives the RAG status throughout the workbook.
Step 2 — TIME TRACKER (update regularly)
Enter Actual Hours logged per team member and your Remaining Hours estimate. Everything else calculates automatically — Forecast Total Hours, Variance, Revenue Billed, and Cost. For Fixed Fee projects, ignore the Revenue columns and focus on cost columns K and L.
Step 3 — COST TRACKER (update as costs are incurred)
Enter Actual to Date and Forecast to Complete for each cost category. Estimated at Completion (EAC) = Actual + FTC — this is your current best estimate of where each cost line will end up. Staff Cost links automatically from the Time Tracker. Variance = Budget minus EAC: positive means under budget, negative means overrun.
Step 4 — PROJECT P&L (read-only, review regularly)
This sheet auto-builds from everything above. Enter Invoiced to Date and Collected to Date (the only manual inputs here). The key number is Forecast GM% at Completion in Column D — this tells you where the project will end up, not just where it is today. Margin Erosion shows the gap vs what you budgeted.
Step 5 — DASHBOARD (share with management or client)
One-page summary with RAG status, all key KPIs, cost breakdown, and dynamic alert messages. The four alerts tell you exactly what action to take — escalate costs, raise an invoice, investigate billing efficiency, or confirm the project is on track.
KEY CONCEPTS
Estimated at Completion (EAC) = Actual Cost to Date + Forecast to Complete. This is what the project will cost in total at current trajectory.
Forecast GM% at Completion = (Contract Value - Total EAC) / Contract Value. This is the single most important number in this template.
Margin Erosion = Forecast GM% - Budgeted GM%. Negative means you will earn less than you priced for — investigate scope creep, cost overruns, or underpricing.
Billing Efficiency = Actual Hours / Budgeted Hours. Below 80% typically means hours are being worked but not captured or billed.
Forecast to Complete (FTC) = your honest current estimate of remaining cost or hours. The accuracy of EAC depends entirely on the quality of your FTC estimate.
HOW DIFFERENT FIRMS SHOULD USE THIS
CA Firms: Track engagement hours per partner/manager/article, fee agreed vs billed vs collected. Focus on billing efficiency and receivables.
IT / Software Firms: Track developer hours against sprint estimates, subcontractor costs, and license costs. EAC on hours is the early warning signal.
Agencies / Consultancies: Fixed-fee retainers — ignore billing rate columns, track only cost per category vs budget. Margin erosion from scope creep shows up immediately in EAC.
Contractors / Project Firms: Track material costs, labour, subcontractors. The four-category cost structure covers most construction and engineering project cost types.
COMPANION TEMPLATES — camsroy.com
AR/AP Tracker Excel: tracks collections from clients — pairs with the Invoiced/Collected rows in this template
Working Capital Gap Calculator: if you run multiple projects, the combined WC gap shows your total funding need
Ratio Analysis / Financial Dashboard: company-level profitability — this template gives you the project-level detail that feeds into it
Copyright 2025 camsroy.com ¦ Free for personal and commercial use ¦ www.camsroy.com